## Sheet1
PRODUCT BACKLOG OF "WEBSITE SUPPORT REGISTER CAMP"
ID | As a / an | I want to… | so that… | notes | acceptance criteria | added in sprint | estimated time | remaining time | priority
1 | The analyst/PO | Analysis Requirements and design website |  |  | Collectively the requirements needed to create a register for camp sites. To be brief idea of the components required in the website | Trung Hieu Hoang | 1 hour |  | 1
2 | Scrum master | Set up Product Backlog & Sprint Backlog |  |  | Set up Product Backlog & Sprint Backlog and Development Team succesful | Nhat Huy Huynh Vo | 3 hour |  | 2
3 | Development Team | Design UI |  |  | Create login interface and site registration | Thanh Phong Do + Kien Ba Dau | 1 day |  | 3
4 | Tester | Check UI |  |  |  | Thanh Lam Do | 2 hour |  | 4
5 | Development Team | Building registration function |  |  |  | Thanh Phong Do + Kien Ba Dau | 1 week |  | 3
6 | Development Team | Build registration function for "organizers" |  |  |  | Thanh Phong Do + Kien Ba Dau | 1 week |  | 3
7 | Tester | Test |  |  |  | Thanh Lam Do | 2 hour |  | 3
8 | Development Team | Build functional interaction with users via Email |  |  |  | Thanh Phong Do + Kien Ba Dau | 1 week |  | 4
9 | Scrum Master + Development Team + Tester | Scrum meeting |  |  | Scrum meeting and update status of the process everyday. | HVNHuy + DTPhong + DBKien + DTLam | 1 hour / 1 day |  | 3
10 | PO + Scrum Master + Development Team + Tester | Sprint: Sum up |  |  | Sum up the process of sprint. If it is over deadline, we have to skip and complete in next sprint | HTHieu + HVNHuy + DTPhong + DBKien + DTLam | 5 hour |  | 5
11 | PO + Scrum Master + Development Team + Tester | Sprint: Meeting and Improve |  |  |  | HVNHuy + DTPhong + DBKien | 5 hour |  | 5
[6 empty] | Total | 23 day + 16 hour