## Sheet1
SPRINT BACKLOG WEEK 1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Designing UI | Task1 | Thanh Phong Do | In Progress | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1
| Task2 | Kien Dau Ba | Waiting | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 1
| Task3 | Thanh Lam Do | Waiting | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 1
Building Data Base | Task1 | Kien Dau Ba | Waiting | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1
| Task2 | Thanh Phong Do | Waiting | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
Coding "Log in and Sig in" | Task1 | Thanh Phong Do | Waiting | 10 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 1
| Task2 | Kien Dau Ba | Waiting | 10 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 1
Test and find mistake | Task1 | Thanh Lam Do | Waiting | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1
|  |  | Total | 35 | 3 | 5 | 10 | 7 | 4 | 10 | 11 | 8